## Project Timeline
NIS
Start Date:
| 0 - 15 |  |  |  | 16 - 30 |  | 31 - 45 | [5 empty] | 46 - 60
TASKS / Days
System Analysis | 9 working days
System Design |  | 9 working days
Architecture |  | 3
Databas |  |  | 2
User Interface |  |  |  | 4
Coding / Customization |  |  |  |  | 14 working days
Coding Environment Setup |  |  |  |  | 2
Forms/Annex Coding | [5 empty] | 12
Legacy Data Import/Exports | [7 empty] | 4
Report Generation | [9 empty] | 14
Standard Reports | [8 empty] | 4
Pivot Table | [9 empty] | 2
Graphs/Charts | [10 empty] | 2
GIS Reports | [11 empty] | 4
Dashboard | [13 empty] | 2
System Testing | [14 empty] | 7
Training | [15 empty] | 2
Hosting / Handover | [16 empty] | 1